## To Do List
CS5100: Foundations of AI
Deadline:
2026-04-15
Diabetic Retinopathy Prediction
Activity | Due By | Owner | Done | Progress | Notes
Team Formation | 2026-02-04 | All | YES | 100% | Team of 3 formed
Project Topic | 2026-02-04 | All | YES | 100% | Diabetic Retinopathy Prediction
Project Proposal | 2026-02-04 | Tanay | YES | 100%
Literature Review | 2026-02-26 | Tanay | YES | 100%
GitHub Repo Created | 2026-03-10 | Ayush | YES | 100% | GitHub Repo will be managed by Ayush. https://github.com/ayumahapat0/diabetic_retinopathy_prediction Access given to each member
Workflow/Pipeline Created | 2026-03-10 | Ayush | YES | 50% | Draft 1 https://lucid.app/lucidchart/0df6059f-298e-4b5b-8d02-86673c52783e/edit?viewport_loc=-172%2C6%2C2319%2C1178%2C0_0&invitationId=inv_324a9058-0953-481d-8b3b-4fa267789363
Image Pre-Processing | 2026-03-11 | Keith | YES | 100%
Data Splitting | 2026-03-11 | Tanay | YES | 100%
GA Optimization | 2026-04-06 | Ayush | YES | 100%
Evaluation | 2026-04-12 | Ayush + Tanay | YES | 100%
First Progress Report | 2026-03-12 | Ayush |  | 100% | The first progress report is due roughly one month before the project.
Final Progress Report | 1969-12-31 19:00 | All |  | 100% | The final progress report is due two weeks before the final submission. For the code portion, please submit all code as it currently stands. For the written portion, write a (brief) description of what you have already completed and what more you plan to do before the final submission.
Final Submission - Code | 2026-03-30 | All |  | 100% | Add Comments, fixed directory paths, add bash script
Final Submission - Paper | 2026-03-30 | All |  | 100% | Introduction, Methods, Results, Conclusions, and Works cited
Formulas:
Due By = [Due By, row below]-14